## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Automative Vehicles Engines
PROJECT MANAGER | Kee Chin Yew
COMPANY NAME | One
DATE | 2023-07-15 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | PARTICIPANTS | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Inititation
1.1 | Title Selection | KEE C Y, FAKHRUL H, NABIL S, SAIFUL A | 2023-06-01 | 2023-06-04 | 3 | 100%
1.2 | Searching Related Article | KEE C Y, FAKHRUL H, NABIL S, SAIFUL A | 2023-06-04 | 2023-06-08 | 4 | 100%
1.3 | Choosing Article | KEE C Y, FAKHRUL H, NABIL S, SAIFUL A | 2023-06-08 | 2023-06-11 | 3 | 100%
2 | Coding
2.1 | Data Gathering | NABIL S | 2023-06-11 | 2023-06-15 | 4 | 100%
2.2 | Data Evaluation | SAIFUL A | 2023-06-15 | 2023-06-19 | 4 | 100%
2.3 | Step by Step Learning | FAKHRUL H | 2023-06-19 | 2023-06-03 | 14 | 100%
2.4 | Analysis | KEE C Y | 2023-07-03 | 2023-07-14 | 11 | 100%
3 | Presentation & Final Submission
3.1 | Slide Preparation | KEE C Y, FAKHRUL H, NABIL S, SAIFUL A | 2023-07-14 | 2023-07-20 | 6 | 80%
3.2 | Report Preparation | KEE C Y, FAKHRUL H, NABIL S, SAIFUL A | 2023-07-14 | 2023-07-25 | 11 | 50%
3.3 | Present the Slide | KEE C Y, FAKHRUL H, NABIL S, SAIFUL A | 2023-07-21 | 2023-07-21 | 0 | 0%
3.4 | Report Submission | KEE C Y | 2023-07-26 | 2023-07-26 | 0 | 0%